## Paper B Tasks
Task ID | Owner | Priority | Task | Instruction | Status | Output path
B1 | R1 | High | Workflow order and reference-standard claim boundary | Check that raw freeze, disagreement, source adjudication, reference freeze, and model comparison are not conflated. | Not started | R1/B1_PaperB_workflow_order_claim_boundary_20260619.md
B2 | R2 | High | Human-human disagreement synthesis | Summarize coder differences by source condition, construct mapping, sample choice, statistic type, and downstream consequence. | Not started | R2/B2_human_disagreement_synthesis_20260619.xlsx
B3 | R3 | High | Source-adjudication gap queue | Identify rows where source-document adjudication or page/table locator evidence remains insufficient. | Not started | R3/B3_source_adjudication_gap_queue_20260619.xlsx
B4 | R4 | High | M1-R results table and appendix package | Convert 2,043-row M1-R denominator-family results into manuscript and appendix-ready tables. | Not started | R4/B4_m1r_results_package_20260619.xlsx
B5 | R1 | High | SEM claim-boundary review | Confirm core-6 diagnostic language and block all-construct/all-row substitution claims. | Not started | R1/B5_sem_claim_boundary_review_20260619.docx
B6 | R4 | Medium | Tables/Figures reader check | Check table order, captions, figure fit, and reader-facing interpretation. | Not started | R4/B6_tables_figures_reader_check_20260619.xlsx
B7 | PI | High | Results final pass | Verify Results text against 2026-06-12 full-corpus files and 2026-06-11/12 TSSEM diagnostics. | Ready for PI review | PI/B7_results_final_pass_20260619.docx
B8 | PI | High | Discussion final pass | Verify no pooled accuracy, vendor-ranking, replacement, or all-row SEM claim remains. | Ready for PI review | PI/B8_discussion_final_pass_20260619.docx
B9 | PI/R4 | High | RSM/GenAI requirements crosswalk | Complete AI-use disclosure, model access date, prompt/parameter note, code/data availability, and public repository boundary. | In progress | PI/B9_rsm_genai_crosswalk_20260619.xlsx

## Summary
Item | Value
Target journal | Research Synthesis Methods
Current goal | Near-submission draft; Results/Discussion strongest sections
Official reference candidate | Paper2 Human Final Consensus v2
Full-corpus M1-R rows | 2043
Allowed main claim | LLM workflow augmentation and review triage
Blocked claims | Pooled accuracy, vendor ranking, autonomous replacement, all-row SEM stability

## RSM Crosswalk
Requirement | Current evidence | Next action
Research design | 213-study source-anchored reference; 2,043-row full-corpus M1-R | Keep dataset/subset counts explicit
Evaluation | Denominator-family accuracy, abstention, exception gates | Report conservative all-scorable interpretation
Validation | Human reference standard and source-document adjudication | Add final PI-approved reference freeze wording
Reproducibility | Locked shards, scripts, manifests, checksums | Refresh public repository manifest if 2026-06-12 files are public
Transparency | Claim-boundary docs | Add final AI disclosure and model access dates